## Sheet1
Project Name | Project Duration | Project Start Date | Project End Date
USAirlineEcho | 13 Weeks | Sep 18, 2023 | Dec 08, 2023
Task ID | Task Description | Task Duration | Start Date | End Date | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-08
1 | Project selection | 1 Week | Sep 18, 2023 | Sep 24, 2023
2 | primary literature review and discussion with Supervisor | 1 Week | Sep 25, 2023 | Oct 01, 2023
3 | Idetifying Gaps and posing Research Questions | 1 Week | Oct 02, 2023 | Oct 08, 2023
4 | Feedback on initial Project proposal | 1 Week | Oct 02, 2023 | Oct 08, 2023
5 | Ethics Submission | 1 Week | Oct 09, 2023 | Oct 15, 2023
6 | Literature Review | 2 Weeks | Oct 16, 2023 | Oct 29, 2023
7 | working on Design Methodology | 2 Weeks | Oct 23, 2023 | Nov 05, 2023
8 | Data Analysis | 1 Week | Nov 06, 2023 | Nov 12, 2023
9 | Feedback from supervior at mid level | 1 Week | Nov 13, 2023 | Nov 19, 2023
10 | Working on Challenges and changes required | 1 Week | Nov 20, 2023 | Nov 26, 2023
11 | Report write up | 1 Week | Nov 27, 2023 | Dec 03, 2023
12 | Feedback from supervisor at Final level | 4 Days | Dec 04, 2023 | Dec 07, 2023
13 | Submission | 1 Day | Dec 08, 2023 | Dec 08, 2023